## 17-239
Task Name | Estimate time( hour) | Taken by | Actual Time | Status | Date Doing | Note | Problem
Requirement analyze | 10 | Nguyen Hoang Nhat Tan | 10 | Done | 2020-03-13
Database design | 12 | Nguyen Hoang Nhat Tan | 14 | Done | 2020-03-14
[UI] Login Form | 1 | Nguyen Hoang Nhat Tan | 1 | Done | 2020-03-16
[UI] Cashier Form | 2 | Nguyen Hoang Nhat Tan | 2 | Done | 2020-03-16
[UI] Admin Form | 0.5 | Nguyen Hoang Nhat Tan | 0.5 | Done | 2020-03-16
[UI] Product Management Form | 2 | Nguyen Hoang Nhat Tan | 2.5 | Done | 2020-03-16
[UI] Order Management Form | 1 | Nguyen Hoang Nhat Tan | 0.5 | Done | 2020-03-17
Functions for Product Management Form (Admin) | 10 | Nguyen Hoang Nhat Tan | 17 | Done | 2020-03-18
Functions for Cashier Form (Cashier) | 12 | Nguyen Hoang Nhat Tan | 10.5 | Done | 2020-03-20
Function for Order Management (Admin) | 2 | Nguyen Hoang Nhat Tan | 1.5 | Done | 2020-03-23
Debug Login functions | 0.5 | Nguyen Hoang Nhat Tan | 1.5 | Done | 2020-03-25
Draw Use Case Diagram | 2 | Nguyen Hoang Nhat Tan | 2.5 | Done | 2020-03-26
Use Case Specifications | 6 | Nguyen Hoang Nhat Tan | 5 | Done | 2020-03-27
Entity Relationship Diagram | 2 | Nguyen Hoang Nhat Tan | 2 | Done | 2020-03-29
Sequence Diagrams | 5 | Nguyen Hoang Nhat Tan | 8.7 | Done | 2020-03-30
3-layer achitecture diagram | 2 | Nguyen Hoang Nhat Tan | 1.5 | Done | 2020-04-02
Total | 70 |  | 142.9% |  | Done task:
Requirement analyze | 10 | Nguyễn Hoàng Phúc Huy | 10 | Done | 2020-03-13
[Report 1] Project Information | 1 | Nguyễn Hoàng Phúc Huy | 1 | Done | 2020-03-13
[Report 1] Current Situation | 1 | Nguyễn Hoàng Phúc Huy | 1 | Done | 2020-03-13
[Report 1] Problem Definition | 2 | Nguyễn Hoàng Phúc Huy | 2 | Done | 2020-03-13
[Report 1] Proposed Solution | 3 | Nguyễn Hoàng Phúc Huy | 3 | Done | 2020-03-13
[Report 1] Functional Requirement | 5 | Nguyễn Hoàng Phúc Huy | 5 | Done | 2020-03-13
[UI] Account Management Form | 2 | Nguyễn Hoàng Phúc Huy | 2 | Done | 2020-03-26
Function for Login Form | 3 | Nguyễn Hoàng Phúc Huy | 3 | Done | 2020-03-13
Function for Account Management Form | 6 | Nguyễn Hoàng Phúc Huy | 6 | Done | 2020-03-27
Debug Add function for Cashier Form | 1.5 | Nguyễn Hoàng Phúc Huy | 1.5 | Done | 2020-03-29
Draw Class Diagram | 3 | Nguyễn Hoàng Phúc Huy | 3 | Done | 2020-03-29
Use Case Specification | 3 | Nguyễn Hoàng Phúc Huy | 3 | Done | 2020-03-29
Interface Design | 4 | Nguyễn Hoàng Phúc Huy | 4 | Done | 2020-04-02
Architectural Model | 1.5 | Nguyễn Hoàng Phúc Huy | 1.5 | Done | 2020-04-03
UserGuide | 3 | Nguyễn Hoàng Phúc Huy | 3 | Done | 2020-04-03
Total | 49 |  | 100% |  | Done task: